## Sheet1
Budget Comparison Tool WP 308
OBJECTIVE 3.1 Budget Controls: The organization has a method for tracking planned expenditures that allows it to compare actual expenditures or outlays to planned or estimated expenditures 2 CFR 200.302(b)(5).
Core Monitoring Guide
3.1.1 The organization has an approved budget that is compared to actual expenditures on a regular basis (i.e., quarterly) to determine if it needs to modify its budget. C
Interview the staff primarily responsible for modifying the budget and comparing budgeted to actual expenditures. Review the organization's most current approved budget.
Does the organization have a current approved budget?
How does the staff compare actual costs to budgeted costs to ensure that the program operates within the budget and the organization submits budget modification requests in a timely manner?
Has the organization done a recent planned vs actual cost analysis?
Does the organization have a method for ensuring that obligations do not exceed availability?
Financial Supplement
In addition to answering the questions below, use the SF-424A and the data in the grantee's books of account to perform a budget-to-actual comparison.
What process does the organization use to tie the account codes used in its internal accounting or budgeting system to the budget categories specified in the grant agreement or contract that it has with the state, DOL, or other entities?
[For discretionary grants only] Does the budget narrative include an adequate explanation of the actual line item costs in the SF424A, including modifications?
Based on the analysis of budget-to-actual, are the items of cost included in appropriate budget line items?
Are managers regularly informed of changes in the budget or given routine updates comparing budgeted items to actual costs?
Are budgets established in conjunction with program delivery and performance goals?
What procedures are in place to handle significant fluctuations in program budgets or spending?
If indirect costs are included on the SF424A, what documentation supports those costs? See also Objective 3.4: Cost Allocation.
Sources and Notes: